Construction Contracts & ICP (Interim Payment Certificates)

So we’re talking construction contracts and ICP = Interim Payment Certificates / Extracts for progress payments based on BOQ, quotations, and POs. Let’s redesign the module specifically for construction / contracting (and treat my previous “rental/subscription” version as discarded for this domain).

Integrated with:

- Projects / Job Costing

- Budgeting & Cost Control

- Purchasing (POs / Subcontracts)

- Finance Lite (AR/AP)

- SAP B1 (Projects, Customers, Vendors, AR/AP docs)

## 1. Scope & Responsibilities (Construction Context)

This module will:

- Manage Main Contracts (Client-side) and Subcontracts (Vendor-side).

- Store BOQ / Bill of Quantities and Contract Values:

  - Items, activities, unit rates, quantities.

- Handle Variations / Change Orders.

- Capture Progress Measurements:

  - Achieved quantities and percentages for each BOQ line / activity.

- Generate Interim Payment Certificates (ICP/IPC):

  - For Client billing (AR certificates).

  - For Subcontractor payments (AP certificates).

- Apply construction financial rules:

  - Retention

  - Advances & advance recovery

  - Deductions (penalties, materials on site, etc.)

- Generate AR/AP documents in SAP B1:

  - AR Invoice / A/R Down Payment / A/R Credit Memos.

  - AP Invoice / AP Credit Memos.

Multi-tenant and multi-company as usual.

## 2. Core Concepts

- Construction Contract (Main / Subcontract)

- BOQ / Bill of Quantities – structured list of items with unit rates.

- Progress Measurement – quantity or % completed per BOQ line, per period.

- ICP / IPC – periodic payment certificate, cumulative and this-period values.

- Retention & Advances – contract-level commercial terms.

- Integration with Projects, Budgeting, Purchasing, SAP B1.

## 3. Data Model

### 3.1 Contract Header (Construction)

Table: ConstructionContracts

| Field | Type |
| --- | --- |
| id | GUID (PK) |
| tenant_id | GUID |
| sap_company_id | GUID |
| code | string |
| name | string |
| contract_role | enum(ContractRole) |
| project_id | GUID |
| sap_project_code | string? |
| client_bp_code | string? |
| subcontractor_bp_code | string? |
| origin_doc_type | enum(OriginDocType)? |
| origin_sap_doc_entry | int? |
| contract_date | date |
| start_date | date |
| end_date_planned | date? |
| end_date_actual | date? |
| currency | string |
| original_contract_sum | decimal |
| revised_contract_sum | decimal |
| retention_percent | decimal? |
| retention_cap_amount | decimal? |
| advance_percent | decimal? |
| advance_amount | decimal? |
| advance_recovery_method | enum(AdvanceRecoveryMethod)? |
| advance_recovery_percent_per_cert | decimal? |
| payment_terms_code | string? |
| status | enum(ConstructionContractStatus) |
| contract_manager_user_id | GUID? |
| engineer_or_consultant_name | string? |
| created_by_user_id | GUID |
| created_at | datetime |
| updated_at | datetime |

ContractRole

- MainContract – you bill the client

- Subcontract – you pay subcontractor

OriginDocType

- SalesQuotation

- PurchaseOrder

- None

ConstructionContractStatus

- Draft

- UnderReview

- Awarded

- Active

- OnHold

- Completed

- Closed

- Terminated

- Cancelled

AdvanceRecoveryMethod

- FixedPercentPerCertificate

- ByProgressTillCertainPercent

- Manual

### 3.2 BOQ (Bill of Quantities)

#### 3.2.1 BOQ Header

Table: BoqHeaders

| Field | Type |
| --- | --- |
| id | GUID (PK) |
| contract_id | GUID |
| code | string |
| name | string |
| revision_no | int |
| is_current | bool |
| created_at | datetime |
| created_by | GUID |

#### 3.2.2 BOQ Items

Table: BoqItems

| Field | Type |
| --- | --- |
| id | GUID (PK) |
| boq_header_id | GUID |
| item_no | string |
| description | string |
| unit | string |
| quantity | decimal |
| unit_rate | decimal |
| line_amount | decimal |
| cost_code | string? |
| project_task_id | GUID? |
| cost_center_code | string? |
| is_provisional_sum | bool |
| is_prime_cost | bool |
| is_active | bool |
| created_at | datetime |
| updated_at | datetime |

Total of BoqItems.line_amount should match original_contract_sum (or be reconciled).

### 3.3 Variations / Change Orders

Table: ContractVariations

| Field | Type |
| --- | --- |
| id | GUID (PK) |
| contract_id | GUID |
| code | string |
| title | string |
| description | string |
| status | enum(VariationStatus) |
| value_change | decimal |
| approved_by_user_id | GUID? |
| approved_at | datetime? |
| created_at | datetime |
| created_by | GUID |

VariationStatus

- Draft

- Submitted

- Approved

- Rejected

- Cancelled

Variations may add/change BoqItems or add separate VariationItems.

### 3.4 Progress Measurements

Measurements of achieved quantity or % complete per BOQ item, per period.

Table: ProgressMeasurementHeaders

| Field | Type |
| --- | --- |
| id | GUID (PK) |
| contract_id | GUID |
| code | string |
| period_start_date | date |
| period_end_date | date |
| measurement_date | date |
| status | enum(MeasurementStatus) |
| engineer_user_id | GUID? |
| created_at | datetime |
| created_by | GUID |
| approved_at | datetime? |
| approved_by | GUID? |

MeasurementStatus

- Draft

- UnderReview

- Approved

- Rejected

Table: ProgressMeasurementLines

| Field | Type |
| --- | --- |
| id | GUID (PK) |
| measurement_header_id | GUID |
| boq_item_id | GUID |
| quantity_this_period | decimal |
| quantity_to_date | decimal |
| percent_complete_to_date | decimal |
| previous_quantity_to_date | decimal |
| line_amount_this_period | decimal |
| line_amount_to_date | decimal |
| remarks | string? |

quantity_to_date = cumulative. System can compute this_period by diff from previous.

### 3.5 ICP / IPC Headers & Lines

#### 3.5.1 ICP Header

Each ICP is a payment certificate referencing one measurement period.

Table: IcpCertificates

| Field | Type |
| --- | --- |
| id | GUID (PK) |
| tenant_id | GUID |
| sap_company_id | GUID |
| contract_id | GUID |
| code | string |
| name | string |
| role | enum(ContractRole) |
| period_start_date | date |
| period_end_date | date |
| certificate_date | date |
| measurement_header_id | GUID? |
| status | enum(IcpStatus) |
| gross_valuation_to_date | decimal |
| gross_valuation_previous | decimal |
| gross_valuation_this_period | decimal |
| retention_percent | decimal |
| retention_to_date | decimal |
| retention_previous | decimal |
| retention_this_period | decimal |
| advance_amount_original | decimal? |
| advance_recovery_to_date | decimal? |
| advance_recovery_previous | decimal? |
| advance_recovery_this_period | decimal? |
| net_certified_this_period | decimal |
| deductions_this_period | decimal |
| payable_this_period | decimal |
| currency | string |
| sap_posting_mode | enum(SapPostingMode) |
| sap_doc_type | string? |
| sap_doc_entry | int? |
| sap_doc_num | int? |
| created_at | datetime |
| created_by_user_id | GUID |
| approved_at | datetime? |
| approved_by_user_id | GUID? |
| workflow_instance_id | GUID? |

IcpStatus

- Draft

- UnderReview

- Certified (approved by engineer/consultant)

- Approved (finance approved to post)

- Invoiced (AR/AP doc created)

- Paid (optional state based on settlement)

- Cancelled

SapPostingMode

- ARInvoice

- APInvoice

- ARDownPayment

- APDownPayment

- JournalEntry (for accruals only)

#### 3.5.2 ICP Lines

Table: IcpCertificateLines

| Field | Type |
| --- | --- |
| id | GUID (PK) |
| icp_certificate_id | GUID |
| boq_item_id | GUID |
| description | string |
| unit | string |
| quantity_contract | decimal |
| unit_rate | decimal |
| quantity_to_date | decimal |
| quantity_previous | decimal |
| quantity_this_period | decimal |
| amount_to_date | decimal |
| amount_previous | decimal |
| amount_this_period | decimal |
| is_provisional_sum | bool |
| is_variation_item | bool |
| created_at | datetime |

There may also be separate lines tables for deductions / additions (retention overrides, penalties, etc.) if needed.

### 3.6 Deductions / Adjustments within ICP

Optional but common:

Table: IcpAdjustments

| Field | Type |
| --- | --- |
| id | GUID (PK) |
| icp_certificate_id | GUID |
| type | enum(IcpAdjustmentType) |
| description | string |
| amount | decimal |
| is_addition | bool |
| created_at | datetime |

IcpAdjustmentType

- MaterialOnSite

- RetentionRelease

- Penalty

- AdvanceRecovery

- Other

## 4. Business Logic / Rules

### 4.1 Contract Creation & BOQ

- Contract can be created:

  - From Sales Quotation (main contract),

  - From Purchase Order (subcontract),

  - Or manually.

- BOQ can be:

  - Imported from Excel,

  - Or derived from Quotation/PO lines.

- original_contract_sum = sum of BOQ items + variations (once approved).

### 4.2 Progress Measurement Rules

- You typically maintain one measurement per period (e.g. monthly).

- For each BoqItem:

  - quantity_to_date <= quantity (unless allowed to exceed for variations).

  - If attempt to measure more: validation error.

- line_amount_this_period = quantity_this_period * unit_rate.

- After measurement approved:

  - It becomes basis for ICP; cannot modify without new measurement or correction entry.

### 4.3 ICP Calculation Logic

For a given contract & period:

- Determine gross valuation:

  - gross_valuation_to_date = sum of BoqItem.amount_to_date (from measurement)

  - gross_valuation_previous = from previous ICP.

  - gross_valuation_this_period = gross_to_date - gross_previous.

- Retention:

  - retention_to_date = gross_valuation_to_date * retention_percent / 100 (subject to cap).

  - retention_previous = from previous ICP.

  - retention_this_period = retention_to_date - retention_previous.

- Advance:

  - If contract has advance:

    - advance_recovery_to_date per rules.

    - advance_recovery_this_period = advance_recovery_to_date - advance_recovery_previous.

- Deductions / Adjustments:

  - Sum of adjustments (penalties, etc.) this period.

- Net certified amount:

  - net_certified_this_period = gross_valuation_this_period - retention_this_period - advance_recovery_this_period + additions - deductions.

- payable_this_period = net_certified_this_period (unless further adjustments / VAT etc. added by Finance).

### 4.4 Posting to SAP B1

- For Main Contracts:

  - ICP results in AR Invoice or AR Down Payment Invoice depending on contract terms.

- For Subcontracts:

  - ICP results in AP Invoice (for paying subcontractor).

Rules:

- Group level:

  - Typically one invoice per ICP per BP, but you may support more granularity.

- IcpCertificateLines map to invoice lines:

  - Either as service lines with description from BOQ items,

  - Or as item lines if you map BOQ items to SAP items.

Retention handling:

- Option A: Post only net payable on invoice, track retention off-books in ICP.

- Option B: Post retention to a retention GL account (credit liability).

## 5. Error Codes (CC-XXX / ICP-XXX)

Contracts / BOQ

- CC-001 CONTRACT_NOT_FOUND

- CC-002 INVALID_CONTRACT_STATUS_TRANSITION

- CC-003 BOQ_ITEM_NOT_FOUND

- CC-004 CONTRACT_SUM_MISMATCH_BOQ

- CC-005 VARIATION_NOT_APPROVED

Measurements / ICP

- ICP-001 MEASUREMENT_NOT_FOUND

- ICP-002 MEASUREMENT_NOT_APPROVED

- ICP-003 QUANTITY_EXCEEDS_CONTRACT

- ICP-004 ICP_ALREADY_EXISTS_FOR_PERIOD

- ICP-005 INVALID_ICP_STATUS_TRANSITION

- ICP-006 SAP_POSTING_FAILED

Example:

{

"errorCode": "ICP-003",

"message": "Measured quantity exceeds contracted quantity for BOQ item 1.2.",

"details": {

"boqItemId": "boq-guid",

"contractQuantity": 1000,

"quantityToDateRequested": 1050

}

}

## 6. Key API Contracts

### 6.1 Create Construction Contract from Quotation or PO

POST /api/construction-contracts

{

"sapCompanyId": "company-guid",

"code": "CC-2026-0001",

"name": "Construction of Warehouse - ABC",

"contractRole": "MainContract",

"projectId": "prj-guid",

"clientBpCode": "C10001",

"originDocType": "SalesQuotation",

"originSapDocEntry": 123,

"contractDate": "2026-01-15",

"startDate": "2026-02-01",

"endDatePlanned": "2027-01-31",

"currency": "EGP",

"retentionPercent": 5,

"advancePercent": 10,

"paymentTermsCode": "NET30"

}

System can then import BOQ from quotation or let user upload separately.

### 6.2 Upload / Update BOQ

POST /api/construction-contracts/{contractId}/boq

{

"code": "BOQ-MAIN",

"items": [

{

"itemNo": "1.1",

"description": "Excavation works",

"unit": "m3",

"quantity": 1500,

"unitRate": 150

},

{

"itemNo": "1.2",

"description": "Concrete works",

"unit": "m3",

"quantity": 800,

"unitRate": 900

}

]

}

### 6.3 Record Progress Measurement

POST /api/construction-contracts/{contractId}/measurements

{

"code": "MEAS-2026-03",

"periodStartDate": "2026-03-01",

"periodEndDate": "2026-03-31",

"measurementDate": "2026-03-30",

"lines": [

{

"boqItemId": "boq1-guid",

"quantityToDate": 500

},

{

"boqItemId": "boq2-guid",

"quantityToDate": 200

}

]

}

Backend:

- Compute quantity_this_period from previous measurements.

- Calculate amounts with unit rates.

- Status = Draft → goes through approval.

### 6.4 Generate ICP from Approved Measurement

POST /api/construction-contracts/{contractId}/icp

{

"measurementHeaderId": "meas-guid",

"certificateDate": "2026-03-31",

"sapPostingMode": "ARInvoice"

}

Backend:

- Validate measurement status Approved.

- Derive cumulative & this-period values.

- Create IcpCertificates + IcpCertificateLines.

- Apply retention, advance recovery, adjustments etc.

Response:

{

"id": "icp-guid",

"code": "IPC-2026-03-001",

"status": "Draft",

"grossValuationThisPeriod": 250000,

"retentionThisPeriod": 12500,

"advanceRecoveryThisPeriod": 20000,

"payableThisPeriod": 217500

}

### 6.5 Approve & Post ICP to SAP

POST /api/icp/{icpId}/approve

{

"comment": "Approved by project manager & finance"

}

Then:

POST /api/icp/{icpId}/post-to-sap

Backend:

- Build SAP AR/AP document from ICP lines.

- Use client_bp_code or subcontractor_bp_code.

- Map to SAP Project & Cost Centers.

Response:

{

"id": "icp-guid",

"status": "Invoiced",

"sapDocType": "OINV",

"sapDocEntry": 5678,

"sapDocNum": 800456,

"amount": 217500

}

### 6.6 Get Contract Progress & ICP Summary

GET /api/construction-contracts/{contractId}/summary

Example:

{

"contractId": "cc-guid",

"code": "CC-2026-0001",

"role": "MainContract",

"projectId": "prj-guid",

"originalContractSum": 1500000,

"revisedContractSum": 1650000,

"currency": "EGP",

"progress": {

"grossValuationToDate": 500000,

"retentionToDate": 25000,

"advanceAmountOriginal": 150000,

"advanceRecoveryToDate": 60000,

"netCertifiedToDate": 415000,

"paidToDate": 350000

},

"lastIcp": {

"code": "IPC-2026-03-001",

"certificateDate": "2026-03-31",

"grossValuationThisPeriod": 250000,

"retentionThisPeriod": 12500,

"advanceRecoveryThisPeriod": 20000,

"payableThisPeriod": 217500

}

}

## 7. Sequence Diagrams (PlantUML) – Construction Version

### 7.1 From Quotation/PO → Contract → Measurement → ICP → SAP Invoice

@startuml

actor "QS/Estimator" as QS

actor "Site Engineer" as SE

actor "Project Manager" as PM

actor "Finance" as FI

participant "Contracts API" as CC

participant "ICP API" as ICP

participant "SAP Connector" as SAP

participant "SAP B1" as B1

' 1) Create contract from quotation

QS -> CC: POST /construction-contracts (from Sales Quotation)

CC -> CC: Create ConstructionContract + BOQ

CC --> QS: Contract Draft

' 2) Contract approval and activation

PM -> CC: Submit contract for approval

CC -> CC: status=UnderReview

FI -> CC: Approve contract

CC -> CC: status=Active

' 3) Monthly measurement

SE -> CC: POST /construction-contracts/{id}/measurements

CC -> CC: Calculate quantities & amounts this period

PM -> CC: Approve measurement

CC -> CC: status=Approved

' 4) Generate ICP

FI -> ICP: POST /construction-contracts/{id}/icp { measurementId }

ICP -> ICP: Build ICP header + lines (gross, retention, advance)

ICP --> FI: ICP Draft

' 5) Approve and post to SAP

FI -> ICP: POST /icp/{icpId}/approve

ICP -> ICP: status=Approved

FI -> ICP: POST /icp/{icpId}/post-to-sap

ICP -> SAP: Create AR Invoice from ICP

SAP -> B1: POST /ServiceLayer/Invoices

B1 --> SAP: DocEntry, DocNum

SAP --> ICP: OK

ICP -> ICP: status=Invoiced, save SAP refs

@enduml

## 8. How It Fits with Your Existing Modules

- Projects / Job Costing

  - Each contract is tied to a project.

  - ICP invoices contribute to project revenue allocations.

  - Subcontractor ICPs contribute to project cost allocations.

- Budgeting & Cost Control

  - Contract values can be imported as project revenue budgets.

  - ICP & AP/AR invoices consume budget and show actual vs budget.

- Purchasing

  - Subcontractor contracts may originate from POs.

  - Subcontractor ICPs result in AP invoices linked to those POs.

- Finance Lite (AR/AP)

  - ICPs drive AR/AP documents in SAP.

  - Finance Lite exposes those invoices with links back to the ICP and contract.